## LTCP-SCHEDULE
City of Napoleon
WWTP & Collection System - Long Term Control Plan Progress Schedule
PROJECT NUMBER | PROJECT NAME | DESCRIPTION | ESTIMATED PROJECT COST | ACTUAL PROJECT COST | SCHEDULED COMPLETION | STATUS
1 | Hilltop Lane Sanitary Sewer Improvements | New 8" sanitary sewer to eliminate discharge from septic systems. Close Hilltop SSO. | 60000 | 94065.33 | 2004 | Complete
2 | Dodd & Yeager Sewer Separation Phase I | New storm and sanitary sewers on Dodd Street, south of Yeager, to remove clean water and new control for CSO. | 225000 | 222187.2 | 2004 | Complete
3 | West Clinton Street Storm Sewer Improvements | Close 12" storm sewer directly connected to sanitary. Close West Clinton SSO. | 40000 | 40000 | 2004 | Complete
4 | West Lift Station Replacement | Upgrade existing PS with new 1.1 MGD pumps and force main. | 348000 | 248263.88 | 2005 | Complete
5 | East Maumee Interceptor | Replace brick sewer east of Perry with new 24". Old sewer left in place for in-line storage. | 418000 | 353875.35 | 2005 | Complete
6 | South Perry Street Pumping Station | New 1.1 MGD PS to lift flows to new East Maumee Interceptor. | 248000 | 377001.66 | 2005 | Complete
7 | Palmer Ditch Pumping Station Control Modifications | Upgrade telemetry at existing PS remote control from WWTP. | 25000 | 25000 | 2005 | Complete
8 | Reiser Street CSO Replacement | New CSO control structure and outfall to eliminate flows into system and relieve localized flooding. | 120000 | 140959 | 2007 | Complete
9 | West Riverview Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I from Sheffield, west along Riverview to Corp Limits. | 175000 | 225000 | 2006 | Complete
10 | Haley Avenue Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I from along Haley Avenue interceptor, from Avon to Sheffield and Riverview to Woodlawn | 85000 | Combined w/ above | 2006 | Complete
11A | West Riverview Interceptor I/I Reduction Projects | Various improvements to remove public and private I/I. Estimate up to 50% removal along Glenwood, 10% - 30% elsewhere. | 525000 | 480487 | 2007 | Complete
11B | West Riverview Interceptor I/I Reduction Projects | Sycamore, Hurst, Martha, Cripple Creek | 525000 | 260588.68 | 2009 | Complete
11C | West Riverview Interceptor I/I Reduction Projects | Deleted Project | 0 | 0 | 2011 | Determined Unnecessary Through the I/I Study.
11D | West Riverview Interceptor I/I Reduction Projects | Deleted Project | 0 | 0 | 2011 | Done as Part of W. Washington Street Project.
11E | West Riverview Interceptor I/I Reduction Projects | Anthony Wayne & Park Lane | 666600 | 0 | 2015
12 | Woodlawn Avenue Sewer Separation | Sewer separation from Scott Street to Haley Avenue. Estimate up to 50% I/I removal. | 360000 | 2333943.08 | 2007 | Complete
13 | South Side Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I south of Maumee River - update of 1980's investigation. | 190000 | 190000 | 2007 | Complete
14 | WWTP Separated System Equalization Basin (2.5 MG) | New 2.5 MG EQ basin for wet weather flows. Store flows for full primary and secondary treatment and disinfection. | 5526000 | 8850000 | 2008 | Complete
15 | West Washington Sanitary Sewer Replacement | Re-route flows along West Washington, east of Haley, to Avon. | 455000 | 3177073.99 | 2009 | Complete
16A | Kenilworth Area I/I Removal Projects (from URS study) | Clairmont Reconstruction from Glenwood to Broadmoor | 750000 | 316399.2 | 2011 | Complete
16B | Kenilworth Area I/I Removal Projects (from URS study) | Sanitary Sewer Creek Crossing, Storm Sewer Outlet, & Waterline replacement | 750000 |  | 2012 | Design started. Estimate = $375,000. Received $225,000 Grant.
16C | Kenilworth Area I/I Removal Projects (from URS study) | Lynne Avenue from Glenwood to Oberhaus Creek | 750000 |  | 2014
16D | Kenilworth Area I/I Removal Projects (from URS study) | Clairmont from Glenwood to Kenilworth | 750000 |  | 2016
16E | Kenilworth Area I/I Removal Projects (from URS study) | Westmont from Broadmoor to Glenwood; Construct Broadmoor from Clairmont to Westmont | 750000 |  | 2018
16F | Kenilworth Area I/I Removal Projects (from URS study) | Westmont from Glenwood to Kenilworth; Kenilworth from Westmont to Clairmont | 750000 |  | 2019
16G | Kenilworth Area I/I Removal Projects (from URS study) | Westchester from Broadmoor to Glenwood; Construct Broadmoor from Westmont to Westchester | 750000 |  | 2021
16H | Kenilworth Area I/I Removal Projects (from URS study) | Westchester from Glenwood to Kenilworth; Kenilworth from Westchester to Westmont | 750000 |  | 2022
16I | Kenilworth Area I/I Removal Projects (from URS study) | Kenilworth from Broadmoor to Glenwood; Construct Broadmoor from Westchester to Chelsea | 750000 |  | 2023
16J | Kenilworth Area I/I Removal Projects (from URS study) | Kenilworth from Glenwood to Westchester | 750000 |  | 2025
17A1 | Haley Avenue Interceptor I/I Reduction Project | Sanitary & Storm on Haley from Washington to Woodlawn; Sanitary & Storm on Clinton from Haley to Scott | 410000 | 854373.83 | 2010 | Complete
17A2 | Haley Avenue Interceptor I/I Reduction Project | Storm & Sanitary on Leonard, High, Lumbard, Woodlawn Court, & Romain (Complete Rebuild of Romain) | 800000 | 894755.33 | 2011 | Complete
17B | Haley Avenue Interceptor I/I Reduction Project | W. Riverview Sanitary & Storm | 583600 |  | 2012 | Revised estimate = $800,000 Construction; $65,000 Design. Received $325,000 Grant.
17C | Haley Avenue Interceptor I/I Reduction Project | Welsted, Strong, Park, Garden, & Sheffield | 501500 |  | 2014 | Revised Estimate = $2,100,000.
17D | Haley Avenue Interceptor I/I Reduction Project | W. Main, Avon Place, Misc. San. MH | 398100 |  | 2016
17E | Haley Avenue Interceptor I/I Reduction Project | W. Riverview Sanitary | 716000 | 0 | 2018 | Determined Unnecessary Through the I/I Study.
18 | West Riverview Interceptor Replacement (Glenwood to Jahns Road) | Enlarge existing 15" sanitary with new 24" sanitary sewer. | 594000 | 491778.47 | 2011 | Complete.
19 | Oberhaus Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I along Oberhaus Interceptor. | 125000 | 225000 | 2012 | Complete.
20A1 | South Side Interceptor I/I Reduction Projects | Various Improvements to remove public and private I/I. Estimate up to 50% removal along East Maumee, 30% removals along Third Street system and near Huddle Road, 10% to 20% elsewhere. Close West Maumee Avenue SSO. | 570000 |  | 2013 | Design to begin in 2013. Revised Construction Estimate = $250,000.
20A2 |  | E. & W. Graceway Storm Sewer Improvements |  | 90865.09 | 2010 | Complete
20A3 |  | S. Perry Street Sanitary Sewer Improvements |  | 174516.4 | 2009 | Complete
20B |  |  | 570000 |  | 2015
20C |  |  | 570000 |  | 2017 | Revised Estimate = $1,500,000.
20D |  |  | 570000 |  | 2019 | Revised Estimate = $1,075,000.
21A | Oberhaus Interceptor I/I Reduction Projects | Various Improvements to remove public and private I/I. Estimate up to 30% removal along low areas from manhole rehabilitation and replacement of creek crossings, 10% to 20% elsewhere. | 375000 |  | 2013 | Design to begin in 2013.
21B |  |  | 375000 |  | 2015
21C |  |  | 375000 |  | 2017
21D |  |  | 375000 |  | 2019
22 | VanHyning Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I along VanHyning Creek. Estimate up to 30% from low areas and creek crossings, as well as along Scott Street commercial area. 10% to 20% removals elsewhere. | 105000 |  | 2016
23 | East Riverview Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I on East Riverview, including the industrial park. | 60000 |  | 2016
24A | VanHyning Interceptor I/I Reduction Projects | Various Improvements to remove public and private I/I. Estimate up to 50% removal along East Maumee, 30% removals along Third Street system and near Huddle Road. 10% to 20% elsewhere. | 315000 |  | 2017
24B |  |  | 315000 |  | 2019
24C |  |  | 315000 |  | 2021
24D |  |  | 315000 |  | 2023
25 | Front Street Interceptor I/I Reduction Study | I/I study to locate sources of public and private I/I along Front Street from Riverview to WWTP. | 25000 |  | 2017
26A | East Riverview Interceptor I/I Reduction Projects | Various Improvements to remove public and private I/I. Estimate 10% to 20% in most areas. | 120000 |  | 2018
26B |  |  | 120000 |  | 2025
27A1 | Dodd & Yeager Sewer Separation Phase II | Storm Sewer Outlet on Rye Street Completed in 2008. |  | 139413.8 | 2008 | Storm Sewer Outlet on Rye Street Completed in 2008.
27A2 | Dodd & Yeager Sewer Separation Phase II | New storm sewers on Yeager, east of Dodd, to remove clean water. Up to 50% I/I reduction. Close Oakwood/Yeager and Dodd/Yeager CSO's. | 500000 |  | 2018
28 | WWTP CSO Treatment Facility or Additional Flow Equalization to Eliminate 602 Outfall. | Flow through primary treatment facility with disinfection for wet weather flows or additional static storage for full secondary treatment and disinfection. | 4503000 |  | 2020
29 | West Riverview Pumping Station, EQ Basin, and 24" Sewer Extension | 750,000 gallon EQ basin, new PS, and 24" sanitary on West Riverview, near Avon. Eliminate existing West Lift Station at Haley Avenue. Close Glenwood Avenue SSO. | 2144500
30 | Avon Place Sanitary Sewer Extension | New 24" sanitary sewer on Avon from Riverview to Washington to disconnect Haley Service Area from Combined Sewers. Close Haley Avenue SSO. | 250000 |  | 2021 | Sanitary Sewer from Avon to W. Washington Done as Part of W. Washington Street Project
31 | Front Street Interceptor I/I Reduction Projects | Additional storm sewers and I/I reduction in East Riverdowns Area. Estimated 10% to 20% I/I reduction. | 150000 |  | 2022
32 | Front Street Interceptor & Palmer Ditch Force Main Relocation | Relocate entry point to WWTP from inside dike to just upstream of new EQ basin and headworks. | 419000 |  | 2024
33 | East Riverview Interceptor Improvements | New 36" sanitary sewer along former DT&I railroad, from East Riverview to WWTP, to re-route flows from Shelby Interceptor to new Separated System EQ basin and headworks. | 341000 |  | 2024
34 | Fillmore Street Sanitary Sewer Improvements | New 15" & 18" sanitary sewers along former DT&I railroad from Vocke Street to East Riverview, to re-route flows from Shelby Interceptor to new Separated System EQ basin and headworks. | 169000 |  | 2024
|  |  | 35566300 | 20205547.29